## TW packages
Ref | Package | Status | Buyer | Enquiry issued | Value £ | Notes
TW01 | Enabling civils, compounds and hardstanding | Tendering | Northern region | 2026-06-02 | 2850000 | Priced from tender layout rev A
TW02 | Cabin hire — offices | Enquiry issued | Northern region | 2026-06-12 | 940000 | Against Cabin Schedule rev A
TW03 | Cabin hire — welfare | Within TW02 | Northern region | 2026-06-12 |  | See TW02
TW04 | Temporary power generation | Enquiry issued | Central plant desk | 2026-07-03 | 3100000 | Sized from services doc rev A, 19 Feb
TW05 | Temporary water and bowser supply | Not started
TW06 | Foul, package plant and tankering | Not started
TW07 | Security — guarding, CCTV, access | Not started
TW08 | Site accommodation (beds, off site) | Not started |  |  |  | Site team to arrange locally
TW09 | Personnel transport / minibuses | Not identified
TW10 | Catering and canteen operation | Not started
TW11 | Cleaning | Not started
TW12 | Waste management | Not started
TW13 | Site comms and IT | Within PW03 | Marrowbridge central
TW14 | Temporary heating and dehumidification | Not identified
TW15 | Fuel storage, dispensing and management | Not identified
TW16 | Wheel wash, dust suppression, road cleaning | Not identified
TW17 | Traffic management (compound gates) | Not started
TW18 | Reinstatement and demobilisation | Assumed within TW01 | Northern region |  |  | No separate allowance
| TOTAL COMMITTED |  |  |  | 6890000
| TOTAL IF ALL LET |  |  |  |  | not recalculated since Aug

## Workforce
Quarter | Civils | M&E | Cable | Converter hall | Staff | Total
2027 Q2 | 46 | 0 | 0 | 0 | 14 | 60
2027 Q3 | 88 | 0 | 6 | 0 | 19 | 113
2027 Q4 | 104 | 0 | 12 | 0 | 22 | 138
2028 Q1 | 96 | 8 | 44 | 12 | 26 | 186
2028 Q2 | 72 | 22 | 61 | 58 | 31 | 244
2028 Q3 | 58 | 40 | 74 | 132 | 36 | 340
2028 Q4 | 44 | 61 | 70 | 126 | 36 | 337
2029 Q1 | 30 | 74 | 58 | 98 | 33 | 293
2029 Q2 | 22 | 66 | 24 | 71 | 28 | 211