## ReadMe
ETABLIX — Five-to-One Consolidation Decision and Cost Model
Companion to ETX-PB-01. Built 08 September 2026. Yellow cells are inputs; everything else is computed.
WHAT THIS ANSWERS
The playbook says consolidate a load problem and not a performance problem, and it says expect a 17–21 per cent wrap.
It cannot say whether the wrap is worth it on YOUR job, because that depends on four sums, a management cost and a
liquidated damages position that are different every time. This model says.
THE SHEETS
Inputs The four transferred sums, the prime's own package, the stack percentages, the client's own management
cost, and the liquidated damages position. Everything else reads from here.
DecisionTest The eight questions at playbook clause 5.3, scored 0/1/2. The verdict is computed, not typed.
LoadModel What the client actually carries with five packages: interfaces, statutory notice deadlines, valuations,
and the management hours behind them, costed. This is the number the wrap is compared against.
WrapCost The four-line stack applied to the transferred value only. Never to the prime's own package.
LDImpact What collapsing four liquidated damages caps into one costs in recoverable damages. Nobody models this
and the prime will not raise it.
Verdict The three numbers side by side, and the answer.
TWO THINGS THIS MODEL WILL NOT DO
It will not tell you to consolidate a performance problem. DecisionTest question 7 fails the whole model if a package is
not performing, and the Verdict sheet says so in words rather than producing a number that flatters the decision.
It will not price the wrap on the prime's own package. That sum was competed in the prime's own tender and charging a
management fee on it is the same money taken twice.
HOW THE FORMULAS WERE CHECKED
LibreOffice cannot recalculate a workbook in the environment this was built in, so every formula is re-implemented
independently in Python and the two are asserted equal before the file is written. A formula that disagrees with its
own re-implementation fails the build rather than shipping.

## Inputs
Inputs
Yellow cells only. Every other sheet reads from here.
Input | Value | Note
THE TRANSFERRED PACKAGES
P1 Civil works — contract sum | 3400000 | Fixed at the cut-off valuation. Never provisional — playbook 8.3.
P2 Modular accommodation — contract sum | 11800000 | Usually the largest of the five.
P3 Kitchen fit-out — contract sum | 1150000
P4 Furniture, fittings and equipment — contract sum | 820000
Number of packages actually transferred | 4 | Set to 3 to model a partial consolidation — playbook 6.4.
THE PRIME'S OWN PACKAGE
P5 FM and operation — contract sum | 6900000 | NOT part of the transferred value. The stack is never applied to it.
THE WRAP
Management and integration | 7% | Playbook range 6–9%. The only line with a headcount behind it.
Corporate overhead recovery | 4% | Range 3–5%.
Profit and prime risk | 6% | Range 5–8%.
Controlled contingency | 4% | Range 3–5%. Not profit — held against the joint register.
Contingency expected to be returned | 50% | Set to 0 if the prime keeps it all; 1 if it is fully returned unused.
THE CLIENT'S OWN COST OF CARRYING FIVE
Months the client would carry the load | 24 | From now to the last practical completion.
Hours per month, per contract administered | 14 | Valuation, notices, change, reporting, correspondence.
Hours per month, per interface held | 9 | Meetings, chasing drawings, reconciling two programmes.
Hours per month, per main-project interface | 5 | The accommodation against the main works.
All-in cost of a client management hour | 78 | Salary, on-costs, overhead — not a charge-out rate.
Cost of one missed pay-less notice | 180000 | The sum applied for becomes payable in full. Size it on one month's application.
Probability of missing one, per notice | 0.4% | 0.4% per deadline. Sixty deadlines a year is not a small number of chances.
DELAY RISK — WHAT SINGLE-POINT ACCOUNTABILITY IS ACTUALLY FOR
Beds in the village | 225
Cost per bed per day if a bed is not available | 145 | Substitute accommodation, subsistence, travel and administration. See the P2 Employer's Requirements.
Months of delay at risk | 1.5 | The realistic exposure if the interfaces are not held.
Probability of that delay with five packages | 35%
Probability of that delay after consolidation | 15% | It does not go to zero. The prime can be late too.
LIQUIDATED DAMAGES
LD cap, per contract | 5% | Five per cent of the contract sum is the common position.
Expected delay exposure, as a share of each cap | 60% | How much of each cap you would realistically be claiming.
Transaction cost of the consolidation | 95000 | Five deeds, four cut-off valuations, and twelve weeks of management time.

## DecisionTest
Decision test
Playbook clause 5.3. Score each line 0, 1 or 2. The verdict is computed.
Question | Score | What a 2 means
Can the client name one person, with time, who holds the ten interfaces? | 2 | No, or the name is someone already full
How many coordination deliverables are overdue? | 2 | Three or more
Has a statutory payment or pay-less notice been missed, or nearly missed? | 1 | Yes, on any package
Are the five progress reports reconciled against one programme every month? | 2 | No, or only sometimes
Is the accommodation competing for the same people as the main project? | 2 | Yes, the same people hold both
Are the four enabling clauses in all five contracts? | 2 | Yes, all four — otherwise read playbook 7.5 first
Is every package performing to its own contract? | 2 | Yes. A 0 here STOPS the model — see the Verdict sheet
Is at least one of the five capable of holding the other four? | 2 | Yes, clearly
Total score, out of 16 |  | 8 or more: consolidate. Below 6: resource the interfaces instead. 6 to 8: consolidate a subset.
Every package performing? |  | Playbook 5.1. Consolidating a performance problem buries it and pays a wrap to acquire it.
Verdict

## LoadModel
What five packages actually cost the client to carry
Interfaces grow as n(n−1)÷2. This is the number the wrap is compared against.
Measure | With five | After | Note
Packages | 5 | 1 | The prime becomes the single counterparty.
Interfaces between packages, n(n−1)÷2 |  | 0 | They do not disappear. They move inside the prime's scope and are priced there.
Interfaces with the main project | 5 | 1
Contracts administered | 5 | 1
Statutory notice deadlines per year (payment + pay-less) |  |  | Miss one pay-less notice and the sum applied for is payable in full.
MANAGEMENT HOURS PER MONTH
Contract administration
Interfaces between packages
Main-project interfaces
Total hours per month |  |  | At the all-in cost on Inputs, not a charge-out rate.
Management cost over the period
Expected cost of missed notices over the period |  |  | Probability × exposure. Not a worst case — an expected value.
TOTAL COST OF CARRYING THE LOAD
Load cost avoided by consolidating |  |  | Management hours and expected notice losses only.
DELAY RISK — the benefit that dwarfs the management hours
Cost of one month of the village being late |  |  | Beds x 30 days x the daily cost of not having one.
Expected delay cost, with five packages
Expected delay cost, after consolidation
Delay risk avoided |  |  | This is what single-point accountability is actually bought for. It is larger than the management saving and it is the line that is never modelled.

## WrapCost
The wrap
Applied to the transferred value only — never to the prime's own package.
Transferred value (the packages actually moving) |  |  | Packages drop off from P4 upward as the transferred count falls.
The prime's own package, excluded |  |  | Already competed in its own tender. A stack on this is the same money taken twice.
Stack line | Rate | Amount | Note
Management and integration |  |  | The only line with a headcount behind it. Ask for names and time.
Corporate overhead recovery |  |  | Lower than a full prime contract — the prime already carries this.
Profit and prime risk |  |  | Should rise if a package is in difficulty and fall if all are performing.
Controlled contingency |  |  | Not profit. Drawn only against the joint register.
TOTAL ADDITION |  |  | Playbook range 17–27%. Expect the lower half on competed prices in good order.
Less contingency expected back |  |  | Unused contingency returned or shared. Zero this if the prime keeps it.
Transaction cost of the transfer |  |  | Five deeds, four cut-off valuations, twelve weeks of management.
NET COST OF CONSOLIDATING |  |  | Compare against LoadModel — the cost avoided.

## LDImpact
Liquidated damages: four caps become one
The prime will not raise this. It is a real reduction in what the client can recover.
Position | Basis | Recoverable | Note
With five separate contracts |  |  | Five caps, five contracts, five independent claims.
After consolidation — one contract with the prime |  |  | One cap on the consolidated sum. Same percentage, one contract.
Difference |  |  | Zero where the cap is a percentage of the whole. It is NOT zero where the prime negotiates a cap in absolute terms — model that below.
IF THE PRIME NEGOTIATES AN ABSOLUTE CAP
Absolute cap the prime asks for | 500000 |  | A single sum, not a percentage. This is the ask to watch for.
Recoverable under an absolute cap
LOST RECOVERY |  |  | Add this to the cost of consolidating. It is as real as the wrap and it is never on the invoice.

## Verdict
The answer
Three numbers, and whether the trade is worth it.
| Amount | Where it comes from
Load cost avoided by consolidating |  | LoadModel — management hours and expected notice losses
Delay risk avoided |  | LoadModel — the larger of the two benefits, and the one usually left out
Net cost of consolidating |  | WrapCost — the stack, less contingency returned, plus the transaction cost
Liquidated damages recovery lost |  | LDImpact — only where the prime negotiates an absolute cap
NET POSITION |  | Positive: the measurable benefits exceed the wrap. Negative: they do not — read the break-even below before concluding anything.
Total measurable benefit |  | Management, notices and delay risk, less the liquidated damages recovery given up.
BREAK-EVEN WRAP RATE |  | The gross stack rate at which consolidation pays for itself on measurable expected value alone. Negotiate toward it, knowing the market sits well above it.
The rate actually offered |  | WrapCost
The gap, in money |  | What the client pays above measurable expected value. It is not waste — it is the price of certainty and of management capacity that cannot be hired. But it should be paid knowingly.
Decision test verdict |  | DecisionTest
THE ANSWER |  | The score and the money have to agree. Where they do not, the sheet says so rather than picking one.
A caution, and it is the point of the model
A positive net position is not a reason to consolidate a performance problem, and the model refuses to give one.
A negative net position is not a reason to refuse a consolidation the decision test says you need: management capacity
you do not have cannot be bought at any rate on the Inputs sheet, and the model cannot see that.
The numbers are here so the decision is argued about with them, not instead of them.
EXPECT THE NET POSITION TO BE NEGATIVE. On measurable expected value a market-rate wrap almost never pays for
itself, and a model that produced a positive number here would be flattering the decision rather than testing it.
What the client buys above the break-even rate is certainty and capacity: single-point accountability, and a management
team it could not hire, assemble and hold for the duration at any rate on the Inputs sheet. That is a real purchase and
it is a legitimate one. It is also the number to take into the negotiation at playbook 8.2 — because a prime that knows
the client has done this arithmetic prices differently from one that assumes it has not.